## Overview
Workshop at University of Graz
Date: March 20-21, 2025
Total Participants: 30
Total Budget: 5000€

## Budget
Category | Item | Calculation | Amount | Subtotal | % of Budget
Travel | International Travel | 2 speakers × 400€ | 800
Travel | Local Travel | 6 speakers × 50€ | 300
Accommodation | Hotel Rooms | 8 speakers × 120€ | 960
Catering | Coffee Breaks | 30 people × 8€ × 3 breaks | 720
Catering | Lunches | 30 people × 18€ × 2 days | 1080
Catering | Speaker Dinner | 8 speakers × 40€ | 320
Materials | Workshop Materials | 30 people × 10€ | 300
Contingency | Contingency Fund | ~10.4% of budget | 520

## Schedule
Time | Duration | Activity | Location | Notes
12:00 | 60min | Registration & Lunch | Main Hall | Check-in and welcome lunch
13:00 | 30min | Welcome & Introduction | Conference Room | Opening remarks
13:30 | 45min | Speaker 1 | Conference Room | Session 1
14:15 | 45min | Speaker 2 | Conference Room | Session 2
15:00 | 30min | Coffee Break | Break Area | Networking
15:30 | 45min | Speaker 3 | Conference Room | Session 3
16:15 | 45min | Speaker 4 | Conference Room | Session 4
17:00 | 15min | Wrap-up Day 1 | Conference Room | Closing remarks
19:00 | 120min | Networking Dinner | Local Restaurant | Speakers only
08:30 | 30min | Morning Coffee | Break Area | Light breakfast
09:00 | 45min | Speaker 5 | Conference Room | Session 5
09:45 | 45min | Speaker 6 | Conference Room | Session 6
10:30 | 30min | Coffee Break | Break Area | Networking
11:00 | 45min | Speaker 7 | Conference Room | Session 7
11:45 | 45min | Speaker 8 | Conference Room | Session 8
12:30 | 30min | Closing Remarks | Conference Room | Summary and farewell
13:00 | 60min | Lunch & Departure | Main Hall | Closing lunch

## Participants
Type | Name | Institution | Email | Dietary Requirements | Travel | Accommodation
International Speaker |  | University TBD |  |  | Flight required | Hotel needed
International Speaker |  | University TBD |  |  | Flight required | Hotel needed
Local Speaker |  | Austrian University |  |  | Train/Bus | Hotel needed

## Checklist
Timeline | Task | Status | Responsible | Due Date | Notes
3 months before | Book venue | Pending |  | 2024-12-20 | University facilities
3 months before | Confirm speakers | Pending |  | 2024-12-20 | Send formal invitations
2 months before | Book catering | Pending |  | 2025-01-20 | Get quotes from local providers
2 months before | Book accommodation | Pending |  | 2025-01-20 | Block book hotel rooms
1 month before | Send final schedule | Pending |  | 2025-02-20 | To all participants
2 weeks before | Confirm all bookings | Pending |  | 2025-03-06 | Double check all arrangements
1 week before | Prepare materials | Pending |  | 2025-03-13 | Print all necessary documents
1 day before | Setup venue | Pending |  | 2025-03-19 | Check AV equipment
Post event | Send thank you notes | Pending |  | 2025-03-22 | To speakers and participants
Post event | Financial reconciliation | Pending |  | 2025-03-28 | Close budget